## Options
Option 1 base case against Option 2 optimised, night shift on trades
Both options use the same trade content, the same crews and the same rates. Only the access arrangement differs.
| OPTION 1 Base case Day shift only, as Draft A | OPTION 2 Optimised Trades day & night, platforms move in daylight only | Note
THE CYCLE
Trade shifts worked per calendar day | 1 | 1.95 | Option 2 adds a night shift on the trades only, derated for night productivity
Effective access days per bent | 2.8571 | 2.8571 | Moves are daylight only in both options. Platform is floating during a move, so it carries the floating availability
Effective trade days per bent | 8.2353 | 4.2232 | Once lifted and transferred onto positive ties the platform is a fixed suspended platform, so trade work carries the fixed availability
Approval hold days | 0 | 0 | Removed in both options if the repair library is agreed under contract Appendix J
EFFECTIVE CYCLE, days per bent | 11.0924 | 7.0804
THE FLEET
Bents per week, one front | 0.54091 | 0.84741
Bents per week required | 4.504 | 4.504 | 227 bents across the two available seasons
WORK FRONTS REQUIRED | 9 | 6 | One front = two floating stage halves working one bent
Stage halves in the water | 18 | 12 | Supplier holds five platforms today. The balance is the fleet build, still POA
Chain blocks required | 36 | 24 | Four Kito 2 t per front
Clamp sets rigged (working plus one bent ahead) | 18 | 12
Campaign weeks | 46.6293 | 44.6457
HEADCOUNT
Trade heads on shift (contractor's cost, not ours) | 45 | 60 | Five trades per face. Option 2 runs two crews per front. Total trade person-shifts is identical at 227 x 7 x 5 = 7,945
Access crew, day shift | 12 | 8 | Riggers, scaffolders, coxswains. A fleet crew, not a per front crew
Access crew, night shift | 0 | 2 | Option 2 only. No moves, no lifting, no man riding at night. Rescue capability and permit control still required
Total on site | 57 | 70
ACCESS COST, our scope only
Access kit | 2266184.8739 | 1446519.7156
Marine base, operating | 3264052.2876 | 3125196.9164 | Largest single line. Rate conflict unresolved
Access labour | 6211025.2101 | 4955669.396 | Charged on campaign weeks, not productive shifts
Fixed access lines | 2480709 | 2480709 | Identical in both options
Subtotal | 14221971.3716 | 12008095.0279
Contingency | 3555492.8429 | 3002023.757 | AACE Class 5
ACCESS TOTAL | 17777464.2145 | 15010118.7849
Access cost per bent | 78314.8203 | 66123.8713
Saving of Option 2 against Option 1 |  | 2767345.4296
WHAT ELSE CHANGES
Marine risk exposure | Moves, lifting and man riding in daylight only | Unchanged. No moves, no lifting, no man riding at night. Night work is trade work on a platform already lifted and tied off, accessed from the jetty deck | Option 2 does not add marine risk, it adds hours on a static platform
Rescue over water | Day only | Required at night as well. The one marine duty that does not go away | Cost carried in the night standby crew above
Recoat window | Blast and first coat can fall either side of a night, risking flash rust and rework | Blast runs into first coat across the day and night boundary, inside the window | The incumbent record already shows defects found after blast, reblast and touch up
Fabrication lead time | More halves to build before a March 2027 mobilisation | Fewer halves. This is the largest programme benefit, not the cost saving | Fleet build is still POA in both options
Accommodation, Ingham | Fewer beds | More beds, and two shift patterns to roster | Trade contractor's cost, but STL will ask
Light spill, marine park | Not applicable | GBRMPA question. The encapsulated habitat contains most of it | Raise in the approvals pathway
Before Option 2 goes to STL, verify: (1) that night work is a choice and not a prohibition under the contract, MSQ, the port authority or GBRMPA, since Draft A states it as a site constraint; (2) the night rescue and medevac arrangement; (3) light spill against the marine park conditions; (4) that the coating supplier supports night application.

## Inputs
ED-018-2026-06 Access Options Model, Rev A
Lucinda jetty remediation. Two access options compared on one basis. Access scope only: trade works are held at the contractor's own durations, crews and rates and are not re-priced.
Blue cells are inputs you may change. Yellow cells are unconfirmed with the owner named. Everything else is formula.
Input | Value | Unit | Source and confidence
Priority bents | 227 | ea | Contract Appendix D priority scope. Planning basis pending the STL bent register
Available weeks | 50.4 | wk | Two 26 week seasons less 1.6 ship call weeks
Working days per week | 6 | d | No Sundays, no seventh day
Access (move) shifts per bent | 2 | sh | Supplier stated: move on 1, move off 1
Trade shifts per bent | 7 | sh | Contractor programme, held identical in both options
Approval hold | 3 | d | Contractor programme column
Repair library agreed (1 yes, 0 no) | 1 | flag | STL decision under contract Appendix J. VERIFY the clause carries the mechanism
Availability: platform floating, during moves | 70% |  | Marine review: floating plant 60 to 80 percent Mar to Nov
Availability: platform fixed on positive ties, trade work | 85% |  | Marine review: fixed suspended platforms 80 to 90 percent
Night crew productivity vs day | 95% |  | Estimate, declared. Option 2 only
Access crew per front | 1.3333 | heads | 12 heads at 9 fronts: riggers, scaffolders, coxswains. Day shift only
Night standby crew: rescue coxswain and crew, permit officer | 2 | heads | Option 2 only. Required, not optional: crews work over water at night
Head day cost | 1850 | $/d | $150/h x 10 h plus $350 LAFHA and remote, GGC rate card
Marine base, operating | 10000 | $/d | ABH SeaLift 6 via T Glenister 20 Aug. CONFLICTS with $32,000/month on file
Access kit per front | 5400 | $/front-wk | Basis: winch set 2,500 + pontoons 1,400 + module 1,500
Contingency | 25% |  | AACE Class 5 screening
Fixed access lines, identical in both options
Line | $ |  | Note
Clamp and suspension certification, lift plans, man-riding certs | 55500 |  | Supplier scope, two engineers
Approvals, inductions, VOCs, first-fit PPE, access crew | 27750 |  | Card 6.1
Blastclad containment skin, $350 x 227 bents | 79450 |  | Containment is part of the platform
Assemble and proof load each front | 66600 |  | 3 riggers and leading hand, 1 shift per front
Marine mobilisation, tow in, establish | 148500 |  | Timing dependent
Kit haulage, 8 semis | 121500 |  | Crawler POA
Rescue proof and cyclone recovery drill | 55500 |  | Gate before the fleet grows
Trial bent proven to the Superintendent | 155400 |  | Calibrates the true cycle
Marine standby through the wet season | 910000 |  | 26 wk at half rate. TBC line by line
Kit standby through the wet season | 475800 |  | Electrical and vehicles off site
Workboat and vehicles | 216209 |  | Does not reconcile to Basis rates, see comment schedule
Demobilise marine and kit | 150000 |  | Timing dependent
Records, MDR, DLP allowance | 18500 |  | Contract 8.1.0
Subtotal, fixed access lines | 2480709
Not priced in either option: fleet build or hire (Activity 2.1, POA, five platforms exist), marine hull and P&I insurances, GBRMPA and MSQ permits, port charges, accommodation, escalation from August 2026 money.

## Sensitivity
Does the answer move? Fronts required under each availability scenario
This is the case for Option 2. Option 1 swings by five fronts across the range; Option 2 holds.
Scenario | Floating availability (moves) | Fixed availability (trade) | Opt 1 cycle, days | Opt 1 FRONTS | Opt 2 cycle, days | Opt 2 FRONTS
Marine review, pessimistic | 60% | 80% | 12.0833 | 10 | 7.8205 | 6
Marine review, mid (model base) | 70% | 85% | 11.0924 | 9 | 7.0804 | 6
Marine review, optimistic | 80% | 90% | 10.2778 | 8 | 6.4886 | 5
Draft A blanket 0.85 | 85% | 85% | 10.5882 | 8 | 6.5762 | 5
Other stresses on Option 2 (mid availability unless stated)
Stress | Opt 2 fronts
Night crew only 80 percent as productive | 6
Marine moves take 3 days, not 2 | 7
Repair library NOT agreed | 8
Scope is 257 bents, not 227 | 7
Pessimistic availability AND no library | 9
A recommendation that holds still when the metocean lands is worth more to a risk averse board than a lower number that moves.

## Levers
Cost optimisation levers, Option 2 base
None of these is claimed in the reported $15.0M. Each is banked only when its verification lands. Blue cells are the lever assumptions.
Lever | Assumption | Saving (incl 25% contingency) | Verification owner
Marine base: moored spud flat top vs manned jack up | $3,000/day vs $10,000/day, 44.5 wks x 7 days | 3522475 | Tim G / ABH quote in writing
Wet season off-hire vs half-rate standby | $250,000 remob lump vs $1,385,800 standby | 1419750 | Supplier off-hire terms; season 2 availability
Night rescue reclassification (upside only) | 2-head night standby crew stood down; fixed workplace ruling | 1235147 | Safety case + regulator; keep in base until cleared
Contingency step down at award | 25% to 15% on firmed subtotal | 1197910 | Class 4 estimate at award
Packages
Package | Access total | Vs $9.3M contract access allowance
Reported base, Option 2 | 14973876 | +$5.7M
Credible: spud + off-hire | 10827901 | +$1.5M
Stretch: + rescue reclassification | 9592754 | +$0.3M
Stretch at 15% contingency | 8825334 | below the allowance
Also assessed: shoulder weeks are weather float, not savings (smaller fleet stretches marine base duration). Single season variant, 11 fronts in 2027 alone: saves about $3.95M operating against ~10 extra stage halves to build (POA) and buys a year of float; price when the fleet build lands. Kit buy vs hire breakeven: about $320,000 per front.